## Instructions
Instructions				As of (latest date in version log):		April 29, 2024

Purpose	This sheet gives details, notes, and instructions that can be helpful to those entering data, viewing data, or in any way using this Google spreadsheet document.

NOTES:
	-	In General, gray-ish colors indicate automated calculations and no values should manually be entered there.
	-	The light yellow fields are where data can and should be entered
	-	Latitude, Longitude coordinates are preferred, but can convert Google Maps links into coordinates also -- it just adds to total time

KEY:

ES-STG2			https://esdevstg546.wpenginepowered.com/
ES-STG			https://elijahstre1stg.wpenginepowered.com/

Basic Sort Process:

1) Sort by DONE low-high
2) Select all rows except the 99s
3) Sort by Priority

## Progress 4-29
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 4-29					AS OF:	April 29, 2024		May 11, 2024

Index	SITE NAMES	SITE-ENV	Project Name	Trello Ticket	Ticket Status	Description	Ticket Type	Project Family	Time Est.	Quick?	Michael's Notes	Priority	Progress	Granular Status	Date Done
1	ElijahStreams	ES-STG2	Create Shortcode Widget: Most Popular videos in last 30 days	94	⛔ Blocked		FEATURE	FILTER, SORT, SEARCH	1 week			03 Medium	3/18 - Ruled out MonsterInsights Popular Posts widget.	10 - Partial
1	ElijahStreams	ES-STG2	AWeber subscriber count auto-update	92	✋🏻 On-Hold	Michael said grab old HACK from orig codebase for ES	FEATURE	SUBSCRIBER COUNT	1 day	Quick 🕓	Pretty Low Priority	04 Low	4/15 - Have been email with API support and the CEO (he reached out to me). Need to create an APP and then authenticate with OAuth2. ON-HOLD to finish working on FILTERS	10 - Partial
2	🌐 MANY SITES	ES-PROD	Google Apps script to copy backups to Google Workspace shared folder	159	✋🏻 On-Hold	UpdraftPlus backup has been working great for almost half a year :) Writing this script may be a moot point, but we will see	MAINT.	WORKFLOW IMPROVEMENT	1 wk		Writing that script is pretty low priority now that the backup is happening in SOME capacity. Much more important things to work on here.	04 Low	Michael said this is lower priority now that I have regular backups scheduled through UpdraftPlus.	10 - Partial
3	🌐 MANY SITES	ES-LARDEV	HOW to sync DATABASE between DEV and STAGING?	190	🚀 In-Progress	We will use DEV (my local computer) to do the updates and push changes to STAGING for review. Once changes are approved, we will push STAGING to PROD	MAINT.	WORKFLOW IMPROVEMENT				04 Low	4/22 - Began researching this in earnest on Friday. It looks like 2 of the most popular "database merging" or "database migration" plugins are WP DB Migrate Pro and WP Vivid. They are both pro, but I'm leaning toward the former based on the different YouTube videos explaining how to use it.	10 - Partial
4	🌐 MANY SITES	ES-PROD	Research hosting our own videos (Bunnynet? Rumble Cloud? Truth Cloud? CloudFlare)	125	⛔ Blocked	Michael has mentioned that we will eventually need to find our own video host	MAINT.	SELF HOSTING	2 hrs			04 Low	4/29 - STARTED. Emailed Michael with findings. ON-HOLD till I hear back from him	10 - Partial
			Menus: Consolidate top nav menu	161
	ElijahStreams	ES-STG	Testimonials PG: ADD Disclaimer that email is private	119
	ElijahStreams	ES-STG	Testimonials PG: ADD verbiage to email TLDRs to info@elijahstreams.com	118
			REMOVE errant comment form on homepage	54
			Branding: Globally remove "Elijah List Ministries" the address heading	209
			Branding: Replace globally ElijahStreams TV -> ElijahStreams	208
			Branding: Replace all instances of "Elijah Streams" with ElijahStreams (no space)	207
			Search PG: Add video filter sidebar	206
			PUT FEELERS out to friends about teaching me Rumble Cloud	205
			Archive Episodes: Add GodTalked as a series	203
			Wells PG: Verify if SmugMug link is working	202
			Archive Episodes: Note which videos need re-uploaded	201
			Backups: Setup UpdraftPlus Dropbox backups	210
5	ElijahStreams	ES-PROD	Fix event infos on older posts	177	⛔ Blocked	ERIC_IDEA: Many of the event info descriptions imported in the older posts have overlapping text and other issues that will require manual intervention	BUG	EVENT INFO	15 min	Quick 🕓	N/A	04 Low	4/30 - EMAILED Michael for feedback on how to proceed	10 - Partial
6	ElijahStreams	ES-STG2	Archive Guests: Sort by most recent video for guest	171	⛔ Blocked	Filtering in in-progress.	FEATURE	FILTER, SORT, SEARCH	2 wk			01 High	3/27 - Filtering almost done	15 - Mostly Done
7	ElijahStreams	ES-STG2	Archive Episodes: Filter by (old) post type (video, live video, etc)	93	✋🏻 On-Hold		FEATURE	FILTER, SORT, SEARCH	2 days			01 High		20 - Unstarted
8	ElijahStreams	ES-STG	Archive Episodes: Filter by host	187	✋🏻 On-Hold	ERIC_IDEA: Have to create a "Host" custom field	FEATURE	FILTER, SORT, SEARCH			Michael liked the idea	01 High		20 - Unstarted
9	ElijahStreams	ES-STG	Archive Episodes: Search filter by episodes and guest names	185	✋🏻 On-Hold		FEATURE	FILTER, SORT, SEARCH				01 High		20 - Unstarted
10	ElijahStreams	ES-STG	Archive Episodes: Add Filter for GodTalked			ERIC_IDEA: By creating new series, we should add a filter for it also	FEATURE	FILTER, SORT, SEARCH				03 Medium		20 - Unstarted
	ElijahStreams	ES-STG2	Search Filtering: Keyword, Author, Posted On, Category [video, word] on search results page	95	✋🏻 On-Hold		FEATURE	FILTER, SORT, SEARCH	1 wk			01 High		20 - Unstarted
	ElijahStreams	ES-STG2	BUG: CPT Video: Make iframe widget height auto fit	151	✋🏻 On-Hold	Custom CSS necessary to make the iframe responsive ruins the ability to plop whatever we want in there	BUG	VIDEO EMBEDS	3 days		Mid Priority, maybe fit in around other larger projects.	03 Medium	3/27 - NOT STARTED: Will work in around other projects	20 - Unstarted
	ElijahStreams	ES-STG	Archive Episodes: Filter by publish date	186	✋🏻 On-Hold		FEATURE	FILTER, SORT, SEARCH				04 Low		20 - Unstarted
11	🌐 MANY SITES	ES-STG	ADMIN: How to use SSH & WP-CLI to manage sites	160	✋🏻 On-Hold	ERIC_IDEA: Probably bit by bit between other tasks	MAINT.	WORKFLOW IMPROVEMENT	1-2wks			04 Low		20 - Unstarted
12	🌐 MANY SITES	ES-LARDEV	HOW to best manage multiple sites in one centralized location?	184		ERIC_IDEA: Probably MainWP. Will need to test	MAINT.	WORKFLOW IMPROVEMENT	1 wk			04 Low		20 - Unstarted
13	ElijahStreams	ES-STG	STG: Wells PG - Replace img grid with Elementor taxonomy grid (sort by country)	199				WELLS PG	1 hr	Quick 🕓		01 High		10 - Partial
14	ElijahStreams	ES-PROD	UpdraftPlus: Increase archive size to reduce total backup files	195		ERIC_IDEA:	MAINT.	WORKFLOW IMPROVEMENT				03 Medium	5/1 - ABANDONED. WPE chat support said 512 MB is the max limit. Any more would need cloud hosting like AWS	95 - Abandoned	5/1/2024
15	ElijahStreams	ES-PROD	Wells Map: Upload new wells	198				WELLS PG	1 hr	Quick 🕓		01 High	5/2 - DONE.	99 - Complete	5/2/2024
16	ElijahStreams	ES-PROD	WELLS PG: UPDATE 05-02-2024	197		* Remove "Salvations" counter / * Update Wells Drilled to 276 / * Update Countries to 12 / * Update People Impacted to 79,800+		WELLS PG	1 hr	Quick 🕓		01 High	5/2 - DONE.	99 - Complete	5/2/2024
17	ElijahStreams	ES-LARDEV	BUG: Testimonials all named Julie	196	🚀 In-Progress	ERIC_IDEA: Although the incoming saved Testimonial posts all have a unique title due the post ID, the name and location part is not working. It is putting “Julie” as the name and location every time.	BUG	SITE PLUGIN				03 Medium	5/2 - DONE. Created a shortcode that rewrites all the testimonial titles. Ran this morning on PROD. Good to go.	99 - Complete	5/2/2024
18	ElijahStreams	ES-LARDEV	Merge Snippets from All Envs together on DEV			Code snippets from STG2 need to be migrated to LARDEV-PROD and converted to site plugin functions.		WORKFLOW IMPROVEMENT				01 High	4/30 - DONE. Uploaded to STG for testing	99 - Complete	4/30/2024
19	ElijahStreams	ES-PROD	Audit ES Site for Accessibility	176		ERIC_IDEA: There are many accessibility considerations we may want to evaluate, the main one being we need an alt tag on each image (except decorative graphics)	MAINT.	A11Y	1 hr	Quick 🕓	N/A	03 Medium	4/26 - DONE. Added filename as ALT tag for each image using plugin Add Image Alt. We may re-visit this later, but the ALT tag was the major component and it is done.	99 - Complete	4/26/2024

## Progress 4-22
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 4-22					AS OF:	April 4, 2024	May 11, 2024

Index	SITE NAMES	SITE-ENV	Project Name	Trello Ticket	Ticket Status	Description	Ticket Type	Time To Complete (Est.)	Quick?	Michael's Notes	Priority	Secondary Priority	Progress	Granular Status	Date Completed
1	ElijahStreams	ES-STG2	BUG: CPT Video: Make iframe widget height auto fit	151	✋🏻 On-Hold	I've looked into this and think I understand the cause. The fix is probably going to related to CUSTOM CSS. It looks like a relatively quick fix, but I'll know more once I begin digging in.	BUG	3 days		Mid Priority, maybe fit in around other larger projects.	03 Medium		3/27 - NOT STARTED: Will work in around other projects	20 - Unstarted
2	ElijahStreams	ES-PROD	BUG: Testimonials all named Julie				BUG				03 Medium			20 - Unstarted
3	ElijahStreams	ES-PROD	Have Michael Review Event Infos imported on older posts	177		ERIC_IDEA: Many of the event info descriptions imported in the older posts have overlapping text and other issues that will require manual intervention	BUG	15 min	Quick 🕓	N/A	04 Low	1		20 - Unstarted
4	ElijahStreams	ES-STG2	Archive Episodes: Filter by (old) post type (video, live video, etc)	93	✋🏻 On-Hold		FEATURE	2 days			01 High			20 - Unstarted
	ElijahStreams	ES-STG	Archive Episodes: Filter by host	187	✋🏻 On-Hold	ERIC_IDEA: Have to create a "Host" custom field	FEATURE			Michael liked the idea	01 High			20 - Unstarted
	ElijahStreams	ES-LARDEV	Merge Snippets from All Envs together on DEV					01 High		4/24 - BEGAN. Migrated PROD 605. Ready to merge snippets	10 - Partial
5	ElijahStreams	ES-STG	Archive Episodes: Filter by publish date	186	✋🏻 On-Hold		FEATURE				04 Low			20 - Unstarted
6	ElijahStreams	ES-STG	Archive Episodes: Search filter by episodes and guest names	185	✋🏻 On-Hold		FEATURE				01 High			20 - Unstarted
7	ElijahStreams	ES-STG2	Archive Guests: Sort by most recent video for guest	171	⛔ Blocked	Filtering in in-progress.	FEATURE	2 wk			01 High	3	3/27 - Filtering almost done	15 - Mostly Done
8	ElijahStreams	ES-STG2	AWeber subscriber count auto-update	92	✋🏻 On-Hold	Michael said grab old HACK from orig codebase for ES	FEATURE	1 day	Quick 🕓	Pretty Low Priority	04 Low	3	4/15 - Have been email with API support and the CEO (he reached out to me). Need to create an APP and then authenticate with OAuth2. ON-HOLD to finish working on FILTERS	10 - Partial
	ElijahStreams	ES-STG2	Create Shortcode Widget: Most Popular videos in last 30 days	94	⛔ Blocked		FEATURE	1 week			03 Medium		3/18 - Ruled out MonsterInsights Popular Posts widget.	10 - Partial
	ElijahStreams	ES-STG2	Search Filtering: Keyword, Author, Posted On, Category [video, word] on search results page	95	✋🏻 On-Hold		FEATURE	1 wk			01 High			20 - Unstarted
	ElijahStreams	ES-PROD	Audit ES Site for Accessibility	176		ERIC_IDEA: There are many accessibility considerations we may want to evaluate, the main one being we need an alt tag on each image (except decorative graphics)	MAINTENANCE	1 hr	Quick 🕓	N/A	03 Medium		3/19 - Michael said go ahead and perform the accessiblility audit	20 - Unstarted
	🌐 MANY SITES	ES-PROD	Google Apps script to copy backups to Google Workspace shared folder	159	✋🏻 On-Hold	UpdraftPlus backup has been working great for almost half a year :) Writing this script may be a moot point, but we will see	MAINTENANCE	1 wk		Writing that script is pretty low priority now that the backup is happening in SOME capacity. Much more important things to work on here.	04 Low	4	Michael said this is lower priority now that I have regular backups scheduled through UpdraftPlus.	10 - Partial
9	🌐 MANY SITES	ES-LARDEV	HOW to sync DATABASE between DEV and STAGING?	190	🚀 In-Progress	We will use DEV (my local computer) to do the updates and push changes to STAGING for review. Once changes are approved, we will push STAGING to PROD	MAINTENANCE				04 Low		4/22 - Began researching this in earnest on Friday. It looks like 2 of the most popular "database merging" or "database migration" plugins are WP DB Migrate Pro and WP Vivid. They are both pro, but I'm leaning toward the former based on the different YouTube videos explaining how to use it.	10 - Partial
10	🌐 MANY SITES	ES-PROD	Research hosting our own videos (Bunnynet? Rumble Cloud? Truth Cloud? CloudFlare)	125		Michael has mentioned that we will eventually need to find our own video host	MAINTENANCE	1 wk			04 Low			20 - Unstarted
11	🌐 MANY SITES	ES-STG	ADMIN: How to use SSH & WP-CLI to manage sites	160	✋🏻 On-Hold	ERIC_IDEA: Probably bit by bit between other tasks	MAINTENANCE	1-2wks			04 Low			20 - Unstarted
12	🌐 MANY SITES	ES-LARDEV	HOW to best manage multiple sites in one centralized location?	184		ERIC_IDEA: Probably MainWP. Will need to test	MAINTENANCE	1 wk			04 Low			20 - Unstarted
	ElijahStreams	ES-PROD	LAUNCH Archive GUESTS: Filter by Primary Roles	191					01 High		4/23 - DONE ~ 8:30 am	99 - Complete	4/23/2024
13	ElijahStreams	ES-PROD	LAUNCH Archive GUESTS: Search filter by guest name	192					01 High		4/23 - DONE ~ 8:30 am	99 - Complete	4/23/2024
	ElijahStreams	ES-PROD	BUG: Archive Guests doesn't sort by vid count correctly	194		For some reason Johnny and Derek are being sorted to the end, when Johnny should be at the top since he has the most videos.		BUG			01 High		4/24 - DONE. The issue was the Jet query and sorting list had "_video_count" meta sort key. Changed to "video_count" and it worked perfectly.	99 - Complete	4/24/2024
	ElijahStreams	ES-PROD	LAUNCH Archive GUESTS: Sort by video count	193					01 High		4/23 - DONE ~ 8:30 am	99 - Complete	4/23/2024
14	ElijahStreams	ES-PROD	LAUNCH Archive Episodes: Filter by Series	189					01 High		4/22 - DONE. Migrated to PROD this morning.	99 - Complete	4/22/2024
15	ElijahStreams	ES-STG	STG: Archive Episodes: Filter by series	188					01 High		4/22 - DONE. Migrated to PROD this morning.	99 - Complete	4/22/2024
16	ElijahStreams	ES-LARDEV	Migrate WPE Environments (PROD, STG, STG2) to LARDEV			ERIC_IDEA: This way we can delete the 2ndary ES site		2 hr		N/A	01 High		4/17 - Finished around 11 AM	99 - Complete	4/17/2024
17	ElijahStreams	ES-LARDEV	Lardev: Streamline child theme styles with SCSS	175		ERIC_IDEA: This is mostly done.		1 wk			01 High		4/16 - Finished & migrated theme to PROD	99 - Complete	4/16/2024
18	ElijahStreams	ES-LARDEV	Lardev: Streamline Code Snippets into Custom Plugin	173		ERIC_IDEA: It looks like just doing a includes/ folder for functions.php in the child theme may be a better way for us. However, if we every change parent theme, a custom plugin will be better		1 wk			01 High		4/16 - Finished & migrated custom plugin to PROD	99 - Complete	4/16/2024
19	ElijahStreams	ES-STG2	ADD Social Share single-button pop-up to Episodes	183					03 Medium		4/15 - DONE. Migrated to Prod. Michael loves it.	99 - Complete	4/15/2024

			KEY:

			ES-STG2			https://esdevstg546.wpenginepowered.com/
			ES-STG			https://elijahstre1stg.wpenginepowered.com/

			Sort Steps:
				1) Sort by DONE low-high
				2) Select all rows except the 99s
				3) Sort by Priority

## Progress 4-16
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 4-16					AS OF:	April 4, 2024	May 11, 2024

Index	SITE NAMES	SITE-ENV	Project Name	Trello Ticket	Ticket Status	Description	Time To Complete (Est.)	Quick?	Michael's Notes	Priority	Secondary Priority	Progress	Granular Status	Date Completed
1	ElijahStreams	ES-STG2	AWeber subscriber count auto-update	92	✋🏻 On-Hold	Michael said grab old HACK from orig codebase for ES	1 day	Quick 🕓	Pretty Low Priority	04 Low	3	4/15 - Have been email with API support and the CEO (he reached out to me). Need to create an APP and then authenticate with OAuth2. ON-HOLD to finish working on FILTERS	10 - Partial
2	ElijahStreams	ES-STG2	Archive Videos: Filter by (old) post type (video, live video, etc)	93	✋🏻 On-Hold		2 days			01 High			20 - Unstarted
3	ElijahStreams	ES-STG2	Create Shortcode Widget: Most Popular videos in last 30 days	94	⛔ Blocked		1 week			03 Medium		3/18 - Ruled out MonsterInsights Popular Posts widget.	10 - Partial
4	ElijahStreams	ES-STG2	Search Filtering: Keyword, Author, Posted On, Category [video, word] on search results page	95	✋🏻 On-Hold		1 wk			01 High			20 - Unstarted
5	🌐 MANY SITES	ES-PROD	Research hosting our own videos (Bunnynet? Rumble Cloud? Truth Cloud? CloudFlare)	125		Michael has mentioned that we will eventually need to find our own video host	1 wk			60 Lowest			20 - Unstarted
6	ElijahStreams	ES-STG2	Make iframe widget height auto fit	151	✋🏻 On-Hold	I've looked into this and think I understand the cause. The fix is probably going to related to CUSTOM CSS. It looks like a relatively quick fix, but I'll know more once I begin digging in.	3 days		Mid Priority, maybe fit in around other larger projects.	03 Medium		3/27 - NOT STARTED: Will work in around other projects	20 - Unstarted
7	ElijahStreams	ES-PROD	Google Apps script to copy backups to Google Workspace shared folder	159	✋🏻 On-Hold	UpdraftPlus backup has been working great for almost half a year :) Writing this script may be a moot point, but we will see	1 wk		Writing that script is pretty low priority now that the backup is happening in SOME capacity. Much more important things to work on here.	04 Low	4	Michael said this is lower priority now that I have regular backups scheduled through UpdraftPlus.	10 - Partial
8	🌐 MANY SITES	ES-STG	ADMIN: How to use SSH & WP-CLI to manage sites	160	✋🏻 On-Hold	ERIC_IDEA: Probably bit by bit between other tasks	1-2wks			03 Medium			20 - Unstarted
9	ElijahStreams	ES-STG2	Archive Guests: Sort by most recent video for guest	171	⛔ Blocked	Filtering in in-progress.	2 wk			01 High	3	3/27 - Filtering almost done	15 - Mostly Done
10	ElijahStreams	ES-PROD	Audit Site for Accessibility	176		ERIC_IDEA: There are many accessibility considerations we may want to evaluate, the main one being we need an alt tag on each image (except decorative graphics)	1 hr	Quick 🕓	N/A	03 Medium		3/19 - Michael said go ahead and perform the accessiblility audit	20 - Unstarted
11	ElijahStreams	ES-PROD	Have Michael Review Event Infos imported on older posts	177		ERIC_IDEA: Many of the event info descriptions imported in the older posts have overlapping text and other issues that will require manual intervention	15 min	Quick 🕓	N/A	04 Low	1		20 - Unstarted
12	🌐 MANY SITES	ES-LARDEV	HOW to best manage multiple sites in one centralized location?	184		ERIC_IDEA: Probably MainWP. Will need to test	1 wk			03 Medium			20 - Unstarted
13	ElijahStreams	ES-STG	Archive Episodes: Search filter by episodes and guest names	185	✋🏻 On-Hold					01 High			20 - Unstarted
	ElijahStreams	ES-STG	Archive Videos: Filter by publish date	186	✋🏻 On-Hold					01 High			20 - Unstarted
14	ElijahStreams	ES-STG	Archive Videos: Filter by host	187	✋🏻 On-Hold	ERIC_IDEA: Have to create a "Host" custom field			Michael liked the idea	01 High			20 - Unstarted
15	ElijahStreams	ES-STG	Archive Episodes: Filter by series	188	⛔ Blocked					01 High		4/18 - SOLVED! It is working on STG. NEXT: Tranfer to PROD	15 - Mostly Done
16	ElijahStreams	ES-LARDEV	Migrate WPE Environments (PROD, STG, STG2) to LARDEV			ERIC_IDEA: This way we can delete the 2ndary ES site	2 hr		N/A	01 High		4/17 - Finished around 11 AM	99 - Complete	4/17/2024
17	ElijahStreams	ES-STG2	ADD Social Share single-button pop-up to Episodes	183					03 Medium		4/15 - DONE. Migrated to Prod. Michael loves it.	99 - Complete	4/15/2024
18	ElijahStreams	ES-LARDEV	Lardev: Streamline child theme styles with SCSS	175	🚀 In-Progress	ERIC_IDEA: This is mostly done.	1 wk			01 High		4/16 - Finished & migrated theme to PROD	99 - Complete	4/16/2024
19	ElijahStreams	ES-LARDEV	Lardev: Streamline Code Snippets into Custom Plugin	173	🚀 In-Progress	ERIC_IDEA: It looks like just doing a includes/ folder for functions.php in the child theme may be a better way for us. However, if we every change parent theme, a custom plugin will be better	1 wk			01 High		4/16 - Finished & migrated custom plugin to PROD	99 - Complete	4/16/2024

			KEY:

			ES-STG2			https://esdevstg546.wpenginepowered.com/
			ES-STG			https://elijahstre1stg.wpenginepowered.com/

			Sort Steps:
				1) Sort by DONE low-high
				2) Select all rows except the 99s
				3) Sort by Priority

## Progress 4-09
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 4-09					AS OF:	April 4, 2024	May 11, 2024

Index	SITE NAMES	SITE-ENV	Project Name	Trello Ticket	Ticket Status	Description	Time To Complete (Est.)	Quick?	Michael's Notes	Priority	Secondary Priority	Progress	Granular Status	Date Completed
1	ElijahStreams	ES-LARDEV	Lardev: Streamline child theme styles with SCSS	175	🚀 In-Progress	ERIC_IDEA: This is mostly done.	1 wk			01 High		4/3 - We need to finish consolidaing CSS	10 - Partial
2	ElijahStreams	ES-LARDEV	Lardev: Streamline Code Snippets into Custom Plugin	173	🚀 In-Progress	ERIC_IDEA: It looks like just doing a includes/ folder for functions.php in the child theme may be a better way for us. However, if we every change parent theme, a custom plugin will be better	1 wk			01 High		4/3 - Custom plugin is created, NEXT: Continue converting code snippets into includes	10 - Partial
3	ElijahStreams	ES-STG2	Archive Guests: Sort by most recent video for guest	171	⛔ Blocked	Filtering in in-progress.	2 wk			01 High	3	3/27 - Filtering almost done	15 - Mostly Done
4	ElijahStreams	ES-STG2	Archive Videos: Filter by (old) post type (video, live video, etc)	93	🚀 In-Progress		2 days			01 High			20 - Unstarted
5	ElijahStreams	ES-STG2	Search Filtering: Keyword, Author, Posted On, Category [video, word] on search results page	95	🚀 In-Progress		1 wk			01 High			20 - Unstarted
6	ElijahStreams	ES-STG2	Create Shortcode Widget: Most Popular videos in last 30 days	94	⛔ Blocked		1 week			03 Medium		3/18 - Ruled out MonsterInsights Popular Posts widget.	10 - Partial
7	ElijahStreams	ES-PROD	Audit Site for Accessibility	176		ERIC_IDEA: There are many accessibility considerations we may want to evaluate, the main one being we need an alt tag on each image (except decorative graphics)	1 hr	Quick 🕓	N/A	03 Medium		3/19 - Michael said go ahead and perform the accessiblility audit	20 - Unstarted
8	🌐 MANY SITES	ES-STG	ADMIN: How to use SSH & WP-CLI to manage sites	160	⛔ Blocked	ERIC_IDEA: Probably bit by bit between other tasks	1-2wks			03 Medium			20 - Unstarted
	ElijahStreams	ES-STG2	ADD Social Share single-button pop-up to Episodes	183					03 Medium			10 - Partial
9	🌐 MANY SITES	ES-LARDEV	HOW to best manage multiple sites in one centralized location?	184		ERIC_IDEA: Probably MainWP. Will need to test	1 wk			03 Medium			20 - Unstarted
10	ElijahStreams	ES-STG2	Make iframe widget height auto fit	151	⛔ Blocked	I've looked into this and think I understand the cause. The fix is probably going to related to CUSTOM CSS. It looks like a relatively quick fix, but I'll know more once I begin digging in.	3 days		Mid Priority, maybe fit in around other larger projects.	03 Medium		3/27 - NOT STARTED: Will work in around other projects	20 - Unstarted
11	ElijahStreams	ES-STG2	AWeber subscriber count auto-update	92	⛔ Blocked	Michael said grab old HACK from orig codebase for ES	2 hr	Quick 🕓	Pretty Low Priority	04 Low	3	4/9 - ADDED code from oldsite to newsite, but its not working for some reason. Will need to troubleshoot. #GOTCHA: It doesn't auto count it just does a cool count up to a fixed number.	10 - Partial
12	ElijahStreams	ES-PROD	Google Apps script to copy backups to Google Workspace shared folder	159	✋🏻 On-Hold	UpdraftPlus backup has been working great for almost half a year :) Writing this script may be a moot point, but we will see	1 wk		Writing that script is pretty low priority now that the backup is happening in SOME capacity. Much more important things to work on here.	04 Low	4	Michael said this is lower priority now that I have regular backups scheduled through UpdraftPlus.	10 - Partial
13	ElijahStreams	ES-PROD	Have Michael Review Event Infos imported on older posts	177		ERIC_IDEA: Many of the event info descriptions imported in the older posts have overlapping text and other issues that will require manual intervention	15 min	Quick 🕓	N/A	04 Low	1		20 - Unstarted
14	🌐 MANY SITES	ES-PROD	Research hosting our own videos (Bunnynet?)	125		Michael has mentioned that we will eventually need to find our own video host	1 wk			60 Lowest			20 - Unstarted
15	ElijahStreams	ES-PROD	Testimonials: ADD Disclaimer that post might not be published and won't be instantaneous (on receipt page)		⛔ Blocked	Disclaimer: Verbiage to inform submitter that their post may or may not be published and it won't be instantaneous			Michael said we are going to call the testimonials feature done after chaning admin email and adding a testimonials@elijahstreams.com notification email	03 Medium		4/9 - EMAILED Michael - He NO to this change. Closed as Abandoned	95 - Abandoned
16	ElijahStreams	ES-STG	Testimonials: ADD disclaimer that email is private	119	⛔ Blocked		15 min	Quick 🕓	Michael said we are going to call the testimonials feature done after chaning admin email and adding a testimonials@elijahstreams.com notification email	04 Low		4/9 - EMAILED Michael - He NO to this change. Closed as Abandoned	95 - Abandoned
17	ElijahStreams	ES-STG	Testimonials: ADD option to submit longer testimonial	118	⛔ Blocked	ERIC_IDEA: Will remove and can add back later if they want, but I think this will help with concerns about inbox management	1 day	Quick 🕓	Michael said we are going to call the testimonials feature done after chaning admin email and adding a testimonials@elijahstreams.com notification email	04 Low		4/9 - EMAILED Michael - He NO to this change. Closed as Abandoned	95 - Abandoned

			KEY:

			ES-STG2			https://esdevstg546.wpenginepowered.com/
			ES-STG			https://elijahstre1stg.wpenginepowered.com/

			Sort Steps:
				1) Sort by DONE low-high
				2) Select all rows except the 99s
				3) Sort by Priority

## Progress 4-03
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 4-03					AS OF:	April 3, 2024	4/3/2024

Index	SITE NAMES	SITE-ENV	Project Name	Trello Ticket	Ticket Status	Description	Time To Complete (Est.)	Quick?	Michael's Notes	Priority	Secondary Priority	Progress	Granular Status	Date Completed
1	ElijahStreams	ES-LARDEV	Lardev: Streamline child theme styles with SCSS	175	🚀 In-Progress	ERIC_IDEA: This is mostly done.	1 wk			01 High		4/3 - We need to finish consolidaing CSS	10 - Partial
2	ElijahStreams	ES-LARDEV	Lardev: Streamline Code Snippets into Custom Plugin	173	🚀 In-Progress	ERIC_IDEA: It looks like just doing a includes/ folder for functions.php in the child theme may be a better way for us. However, if we every change parent theme, a custom plugin will be better	1 wk			01 High		4/3 - Custom plugin is created, NEXT: Continue converting code snippets into includes	10 - Partial
3	ElijahStreams	ES-STG2	Archive Guests: Sort by most recent video for guest	171	⛔ Blocked	Filtering in in-progress.	2 wk			01 High	3	3/27 - Filtering almost done	15 - Mostly Done
4	ElijahStreams	ES-STG2	Archive Videos: Filter by (old) post type (video, live video, etc)	93	🚀 In-Progress		2 days			01 High			20 - Unstarted
5	ElijahStreams	ES-STG2	Search Filtering: Keyword, Author, Posted On, Category [video, word] on search results page	95	🚀 In-Progress		1 wk			01 High			20 - Unstarted
6	ElijahStreams	ES-STG2	Create Shortcode Widget: Most Popular videos in last 30 days	94	⛔ Blocked		1 week			03 Medium		3/18 - Ruled out MonsterInsights Popular Posts widget.	10 - Partial
7	ElijahStreams	ES-PROD	Audit Site for Accessibility	176		ERIC_IDEA: There are many accessibility considerations we may want to evaluate, the main one being we need an alt tag on each image (except decorative graphics)	1 hr	Quick 🕓	N/A	03 Medium		3/19 - Michael said go ahead and perform the accessiblility audit	20 - Unstarted
8	🌐 MANY SITES	ES-STG	ADMIN: How to use SSH & WP-CLI to manage sites	160	⛔ Blocked	ERIC_IDEA: Probably bit by bit between other tasks	1-2wks			03 Medium			20 - Unstarted
9	ElijahStreams	ES-STG2	Make iframe widget height auto fit	151	⛔ Blocked	I've looked into this and think I understand the cause. The fix is probably going to related to CUSTOM CSS. It looks like a relatively quick fix, but I'll know more once I begin digging in.	3 days		Mid Priority, maybe fit in around other larger projects.	03 Medium		3/27 - NOT STARTED: Will work in around other projects	20 - Unstarted
10	ElijahStreams	ES-PROD	Testimonials: ADD Disclaimer that post might not be published and won't be instantaneous (on receipt page)			Disclaimer: Verbiage to infor submitter that their post may or may not be published and it won't be instantaneous				03 Medium			20 - Unstarted
11	🌐 MANY SITES	ES-LARDEV	HOW to best manage multiple sites in one centralized location?	Need Ticket		ERIC_IDEA: Probably MainWP. Will need to test	1 wk			03 Medium			20 - Unstarted
12	ElijahStreams	ES-STG2	AWeber subscriber count auto-update	92	⛔ Blocked	Michael said grab old HACK from orig codebase for ES	2 hr	Quick 🕓	Pretty Low Priority	04 Low	3	4/8 - STARTED. Located HTML and JS neeeded. NEXT, migrate to a text widget	10 - Partial
13	ElijahStreams	ES-PROD	Google Apps script to copy backups to Google Workspace shared folder	159	✋🏻 On-Hold	UpdraftPlus backup has been working great for almost half a year :) Writing this script may be a moot point, but we will see	1 wk		Writing that script is pretty low priority now that the backup is happening in SOME capacity. Much more important things to work on here.	04 Low	4	Michael said this is lower priority now that I have regular backups scheduled through UpdraftPlus.	10 - Partial
14	ElijahStreams	ES-PROD	Have Michael Review Event Infos imported on older posts	177		ERIC_IDEA: Many of the event info descriptions imported in the older posts have overlapping text and other issues that will require manual intervention	15 min	Quick 🕓	N/A	04 Low	1		20 - Unstarted
15	ElijahStreams	ES-STG	Testimonials: ADD disclaimer that email is private	119	⛔ Blocked		15 min	Quick 🕓		04 Low			20 - Unstarted
16	ElijahStreams	ES-STG	Testimonials: ADD option to submit longer testimonial	118	⛔ Blocked	ERIC_IDEA: Will remove and can add back later if they want, but I think this will help with concerns about inbox management	1 day	Quick 🕓		04 Low			20 - Unstarted
17	🌐 MANY SITES	ES-PROD	Research hosting our own videos (Bunnynet?)	125		Michael has mentioned that we will eventually need to find our own video host	1 wk			60 Lowest			20 - Unstarted
18	ElijahStreams	ES-PROD	Create Guest Posts for missing / new guests	104	⛔ Blocked		1 hr	Quick 🕓		03 Medium		4/8 - DONE	99 - Complete	4/8/2024
19	ElijahStreams	ES-PROD	Testimonials: Ensure the "required" asterisk shows up for consent checkbox	182				Quick 🕓		01 High		4/8 - DONE	99 - Complete	4/8/2024
20	🌐 MANY SITES		PODCAST: Add Maintenance page to all podcast sites (3)	178		Michael requested today. I'll start with ElijahForce, then do ElijahFire and ElijahStreams	2 hr	Quick 🕓	If you could put a maintenance message up that would be great. In fact if you could do that on all of the podcasting sites for the homepage that would be awesome.	01 High		4/4 - DONE	99 - Complete	4/4/2024
21	ElijahStreams	ES-PROD	BRANDING: Replace "Elijah Streams" in Episode Titles	179		* https://elijahstreams.com/videos/flash-eric-trump-is-on-elijah-streams-thursday-morning-8am-pt/ * https://elijahstreams.com/videos/urgent-heres-where-to-watch-elijah-streams-right-now/	15 min	Quick 🕓		01 High		4/8 - DONE	99 - Complete	4/8/2024
22	ElijahStreams	ES-PROD	BRANDING: Replace "Elijah Streams" on Steve's host page	180		https://elijahstreams.com/guests/steve-shultz/	1 hr	Quick 🕓		01 High		4/8 - DONE	99 - Complete	4/8/2024
23	ElijahStreams	ES-PROD	Testimonials: Add testimonial CTA to homepage sidebar	181			15 min	Quick 🕓				4/8 - DONE	99 - Complete	4/8/2024
	ElijahStreams	ES-PROD	Change branding sitewide from "Elijah Streams" to ElijahStreams (no space)	174					01 High		3/27 - DONE	99 - Complete	3/27/2024
	🎤 ElijahForce Podcast	EFORCE-PROD	CREATE SITE: ElijahForcePodcast.com			Hey Eric! We’re needing a new podcast site setup to accommodate the new show we’re launching on Monday, ElijahForce! I’d like you to setup essentially a carbon copy of the ElijahStreams/ElijahFire podcasting sites on a new domain I just bought. ElijahForcePodcast.com. It’s under the Ministry login on IONOS. We’ll need this setup no later than Friday morning so Mariah can get podcasts uploaded by end of day Friday. Let me know if you have any questions. It’s just a bare bones WordPress install, so it shouldn’t be too complicated.				01 High		4/03 - DONE! Started yesterday, finsihed today. Emailed Michael. Mariah said it looks good. No Ticket	99 - Complete	4/3/2024
	ElijahStreams	ES-PROD	Launch Testimonials on PROD					01 High		3/27 - Preparing today to launch tomorrow morning	99 - Complete	3/27/2024
	ElijahStreams	ES-PROD	Testimonials: Remove verbiage about sending a longer testimonial to email			ERIC_IDEA: Will remove and can add back later if they want, but I think this will help with concerns about inbox management				01 High		4/1 - DONE. No ticket	99 - Complete	4/1/2024

			KEY:

			ES-STG2			https://esdevstg546.wpenginepowered.com/
			ES-STG			https://elijahstre1stg.wpenginepowered.com/

			Sort Steps:
				1) Sort by DONE low-high
				2) Select all rows except the 99s
				3) Sort by Priority

## Progress 3-27
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 3-27				AS OF:	March 27, 2024			3/27/2024

Index	Project Name	Description	Time To Complete	Michael's Notes	Priority	Secondary Priority	Progress	SITE NAMES	SITE-ENV	DONE	Date Completed
1	Filter Archive: Guests	Filtering in in-progress.			01 High	3	3/27 - Filtering almost done	ElijahStreams	STG2	15 - Mostly Done
2	Filter Archive: Episodes	Filtering in in-progress.			01 High		3/27 - ???	ElijahStreams	STG2	15 - Mostly Done
	Create Shortcode Widget: Most Popular videos in last 30 days				03 Medium		3/18 - Ruled out MonsterInsights Popular Posts widget.	ElijahStreams	STG2	10 - Partial
	Remove verbiage about sending a longer testimonial to email	ERIC_IDEA: Will remove and can add back later if they want, but I think this will help with concerns about inbox management			01 High			ElijahStreams		20 - Unstarted
	Streamline Code Snippets into Custom Plugin				01 High		3/27 - Custom plugin is created, next we need to create individual files to include_once.	ElijahStreams	LARDEV	10 - Partial
	Create Guest Posts for missing guests				03 Medium			ElijahStreams	PROD
	Episodes Filter: Sort by Guests with Recent Appearance				03 Medium		3/27 - In progress. Gotcha: NOT WORKING yet. Next, resume exploring options	ElijahStreams	STG2	10 - Partial
3	Launch Testimonials on PROD				01 High		3/27 - Preparing today to launch tomorrow morning	ElijahStreams	PROD	15 - Mostly Done
4	Audit Site for Accessibility	ERIC_IDEA: There are many accessibility considerations we may want to evaluate, the main one being we need an alt tag on each image (except decorative graphics)		N/A	03 Medium		3/19 - Michael said go ahead and perform the accessiblility audit	ElijahStreams	PROD	20 - Unstarted
5	Make iframe widget height auto fit	I've looked into this and think I understand the cause. The fix is probably going to related to CUSTOM CSS. It looks like a relatively quick fix, but I'll know more once I begin digging in.	(1hr-2dy)	Mid Priority, maybe fit in around other larger projects.	03 Medium		3/27 - NOT STARTED: Will work in around other projects	ElijahStreams		20 - Unstarted
6	AWeber subscriber count auto-update	Michael said grab old HACK from orig codebase for ES	(1dy-1wk)	Pretty Low Priority	04 Low	3	3/27 - Not started	ElijahStreams	STG2	10 - Partial
7	Google Apps script to copy backups to Google Workspace shared folder	Scheduled UpdraftPlus backup has been working for 3 months	(2dy-1wk)	Writing that script is pretty low priority now that the backup is happening in SOME capacity. Much more important things to work on here.	04 Low	4	Michael said this is lower priority now that I have regular backups scheduled through UpdraftPlus.	ElijahStreams	PROD	10 - Partial
8	Have Michael Review Event Infos imported on older posts			N/A	04 Low	1		ElijahStreams	PROD	20 - Unstarted

	KEY:

	STG2	https://esdevstg546.wpenginepowered.com/
	STG	https://elijahstre1stg.wpenginepowered.com/

	Sort Steps:
		1) Sort by DONE low-high
		2) Select all rows except the 99s
		3) Sort by Priority

## Progress 3-20
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 3-20				AS OF:	February 2, 2024		3/20/2024

Index	Project Name	Description	Time To Complete	Michael's Notes	Priority	Secondary Priority	Progress	SITE-ENV	DONE	Date Completed
1	Configure GitHub to work with WPE ES	It may be that we don't really need GitHub, as long as I have Git on my laptop? NO, we should have the repo somewhere safe where anyone else who needs to work on it can, or in case my hard drive dies, etc.	(2dy-2wk)	N/A	01 High	4	3/19 - Advised Michael, but it seems like he is not interested in GitHub account because he thinks the GDrive backup should be sufficient. ABANDONED as unnecessary.		99 - Yes
2	Front end filtering of search results	Filtering is going great. Not trivial by any means.	(1-2wk)	This should be near the top of the priority list along with the filtering below. I was under the impression that those two were part of the same project in all of our previous discussions…	01 High	3	3/19 - Michael liked the feature, but had a few tweak requests. NEXT: Implement Michaels requested changes	STG2	15 - Mostly Done
3	Audit Site for Accessibility	ERIC_IDEA: There are many accessibility considerations we may want to evaluate, the main one being we need an alt tag on each image (except decorative graphics)		N/A	03 Medium		3/19 - Michael said go ahead and perform the accessiblility audit		20 - Unstarted
4	Make iframe widget height auto fit	I've looked into this and think I understand the cause. The fix is probably going to related to CUSTOM CSS. It looks like a relatively quick fix, but I'll know more once I begin digging in.	(1hr-2dy)	Mid Priority, maybe fit in around other larger projects.	03 Medium		Will work in around other projects		20 - Unstarted
5	Google Apps script to copy backups to Google Workspace shared folder	Scheduled UpdraftPlus backup has been working for 3 months	(2dy-1wk)	Writing that script is pretty low priority now that the backup is happening in SOME capacity. Much more important things to work on here.	04 Low	4	Michael said this is lower priority now that I have regular backups scheduled through UpdraftPlus.		10 - Partial
6	AWeber subscriber count auto-update	I came across an article on AWeber yesterday that explains how to do this. The next steps is just to implement it and test. Which I can probably do tomorrow.	(1dy-1wk)	Pretty Low Priority	04 Low	3	3/19 - Michael advised to pull HACK code from original ES website codebase		10 - Partial
7	Testimonials Page	Michael basically said to undo most of the changes Peter requested. He requested a list of all-in-one testimonials plugins, which I sent along with my recommendation to purchase Strong Testimonials. His card wasn't working so it didn't look like he'd get to it this week.		N/A	01 High	2	3/19 - Undid most of Peter's changes, as requested by Michael	STG	99 - Yes
8	Post Revisions Not Showing	I thought we had fixed this already, but despite having revisions enabled, they don't appear to be. My guess is -- as sometimes happens -- there are multiple controls that govern this feature and one I'm not aware of is overriding. I'll know more once I start digging in.		I would call this medium importance, defiantly higher than things like the AW subscriber count and missing event info. We need to be able to see versions easily.	03 Medium		3/19 - THIS FEATURE IS COMPLETED and I have advised Michael that WPE controls it		99 - Yes
9	Missing event info on videos			N/A	04 Low	1	3/7 - This is done, but Michael probably should look at the results to confirm done to his liking		99 - Yes
10	Update Wells page based on Google Sheet	I have set a reminder schedule to tackle these updates on the first of each month, and I worked on this yesterday.	(2hrs-1day)	Great, looking forward to this.	02 High - Regularly Scheduled	1	3/19 - Advised Michael, but there has been no movement of any updates from the Salleys		99 - Yes

	KEY:

	STG2	https://esdevstg546.wpenginepowered.com/
	STG	https://elijahstre1stg.wpenginepowered.com/

## Progress 3-6
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 3-6				AS OF:	February 2, 2024

Index	Project Name	Description	Time To Complete	Michael's Notes	Priority	Secondary Priority	Progress	SITE-ENV	DONE	Date Completed
1	Configure GitHub to work with WPE ES	It may be that we don't really need GitHub, as long as I have Git on my laptop? NO, we should have the repo somewhere safe where anyone else who needs to work on it can, or in case my hard drive dies, etc.	(2dy-2wk)	N/A	01 High	4	Need to let Michael know benefits of GitHub and see if he wants to create an account		10 - Partial
2	Front end filtering of search results	Filtering is going great. Not trivial by any means.	(1-2wk)	This should be near the top of the priority list along with the filtering below. I was under the impression that those two were part of the same project in all of our previous discussions…	01 High	3	3/7 - Filtering for guests page is done (STG2), but need approval from Michael	STG2	15 - Mostly Done
3	Audit Site for Accessibility	ERIC_IDEA: There are many accessibility considerations we may want to evaluate, the main one being we need an alt tag on each image (except decorative graphics)		N/A	03 Medium				20 - Unstarted
4	Make iframe widget height auto fit	I've looked into this and think I understand the cause. The fix is probably going to related to CUSTOM CSS. It looks like a relatively quick fix, but I'll know more once I begin digging in.	(1hr-2dy)	Mid Priority, maybe fit in around other larger projects.	03 Medium		Will work in around other projects		20 - Unstarted
5	Google Apps script to copy backups to Google Workspace shared folder	Scheduled backup of ElijahStreams.com to my EricH@ElijahStreams.com account has been working fine for ten days (since 1/22), though manual copying from Google Drive to the shared Google Workspace folder is still required. I've been exploring automation solutions and it looks like the easiest solution may be a custom Google Apps script. I wrote a script that successfully copies files from one folder to another on the same Google Drive. Next steps: Test copying to a folder on a different drive. Potential roadblocks: I can foresee authentication being an issue -- I'll know more as I dig in.	(2dy-1wk)	Writing that script is pretty low priority now that the backup is happening in SOME capacity. Much more important things to work on here.	04 Low	4	Michael said this is lower priority now that I have regular backups scheduled through UpdraftPlus.		10 - Partial
6	AWeber subscriber count auto-update	I came across an article on AWeber yesterday that explains how to do this. The next steps is just to implement it and test. Which I can probably do tomorrow.	(1dy-1wk)	Pretty Low Priority	04 Low	3	3/15 - Tried the steps listed here: https://help.aweber.com/hc/en-us/articles/204027696-How-do-I-add-a-subscriber-counter-to-my-form-or-website. This only generates a fixed image with tiny font - it is not auto-updated. May need to refer to API. Tix: https://trello.com/c/C9qcIE8N/92-stg-add-auto-updated-aweber-subscriber-count-to-homepage		10 - Partial
7	Testimonials Page	Michael basically said to undo most of the changes Peter requested. He requested a list of all-in-one testimonials plugins, which I sent along with my recommendation to purchase Strong Testimonials. His card wasn't working so it didn't look like he'd get to it this week.		N/A	01 High	2	3/7 - Done, but need final approval from Michael. After approval, will likely take 2hours - 2 days to complete launching the feature	STG	99 - Yes
8	Post Revisions Not Showing	I thought we had fixed this already, but despite having revisions enabled, they don't appear to be. My guess is -- as sometimes happens -- there are multiple controls that govern this feature and one I'm not aware of is overriding. I'll know more once I start digging in.		I would call this medium importance, defiantly higher than things like the AW subscriber count and missing event info. We need to be able to see versions easily.	03 Medium		3/15 - SOLVED! Had to ask WPE support to turn on as they are disabled by default to help avoid site performance impact		99 - Yes
9	Missing event info on videos			N/A	04 Low	1	3/7 - This is done, but Michael probably should look at the results to confirm done to his liking		99 - Yes
10	Update Wells page based on Google Sheet	I have set a reminder schedule to tackle these updates on the first of each month, and I worked on this yesterday.	(2hrs-1day)	Great, looking forward to this.	02 High - Regularly Scheduled	1	2/2 - Michael liked it, but he wanted the colors changed to a single color for each country		99 - Yes

	KEY:

	STG2	https://esdevstg546.wpenginepowered.com/
	STG	https://elijahstre1stg.wpenginepowered.com/

## Progress 2-2
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 2-2				AS OF:	February 2, 2024

Index	Project Name	Description	Time To Complete	Michael's Notes	Priority	Secondary Priority	Progress	DONE	Date Completed
1	Testimonials Page	Peter and I both liked the idea of having everything (the testimonials and the form) on one page, but it sounds like the Salley's want two pages (one for Testimonies and Donations and one just for testimonial submission form)? That shouldn't be any problem -- I'd just need some clarity on what the vision for each page is. Are there specific ideas for layout, user journey (the desired sequence of steps for the visitor), or anything else that I should be aware of in order to get it incorporated into the final deliverables?	(2d-2wk)	[Michael asked Peter to send let me know which pieces from his examples he wants to implement]	01 High	2	2/6 - Awaiting feedback from Peter on what pieces fro the examples he wants to implement. Need to fix the randomizing post feature	10 - Partial
2	Configure GitHub to work with WPE ES	I discovered that one recommended approach for using source control with WordPress and WPE is to use GitHub Actions with a YML config file to automate pushing to a server. It is not a trivial process to setup, but it works great once configured. Another approach is just to not use automation but use GitHub for source control anyway. We probably would want to create a private Enterprise-level GitHub account if we don't have one already for either approach. We will be able to use GitHub/Git for developing custom CSS and custom PHP. For now I would recommend sticking with just using GitHub for version control and we can look into implementing the automation part later.	(2dy-2wk)	When you say automatic pushing, what do you mean with that? Like pressing a button and pushing the code changes to the site? What’s the point of GitHub without that?	01 High	4		10 - Partial
3	Front end filtering of search results	I've got a good idea of the approach to take using Crocoblock plugins. Next steps: Implement and test my theories on STAGING.	(1-2wk)	This should be near the top of the priority list along with the filtering below. I was under the impression that those two were part of the same project in all of our previous discussions…	01 High	3	1/26 - Began researching options (esp: https://www.youtube.com/watch?v=EBj7nmSxbuk&t=2211s)	20 - Unstarted
4	Filters in sidebar	We have the plugins we need to implement this and next steps is begin testing various solutions.	(1-2wk)		01 High	3	1/26 - Began researching options	20 - Unstarted
5	Post Revisions Not Showing	I thought we had fixed this already, but despite having revisions enabled, they don't appear to be. My guess is -- as sometimes happens -- there are multiple controls that govern this feature and one I'm not aware of is overriding. I'll know more once I start digging in.		I would call this medium importance, defiantly higher than things like the AW subscriber count and missing event info. We need to be able to see versions easily.	03 Medium			20 - Unstarted
6	Audit Site for Accessibility	Eric: There are many accessibility considerations we may want to evaluate, the main one being we need an alt tag on each image (except decorative graphics)		N/A	03 Medium			20 - Unstarted
7	Make iframe widget height auto fit	I've looked into this and think I understand the cause. The fix is probably going to related to CUSTOM CSS. It looks like a relatively quick fix, but I'll know more once I begin digging in.	(1hr-2dy)	Mid Priority, maybe fit in around other larger projects.	03 Medium		Will work in around other projects	20 - Unstarted
8	Missing event info on videos	I had already recovered ~500/580 missing event infos on STAGING on 1/19 (before your email saying to treat as low priority) and the data is in a CSV ready to import into PROD when you give the go ahead. I have left this alone since then to working on higher priority projects. When you are ready, we should probably schedule a couple hours for maintenance, although I expect it shouldn't take that long. What I have available for older posts in a lot of cases is a field called "blurb", so it doesn't look exactly like our "next info" field I introduced last year.	(1hr-3wks)	If this is only a couple hours’ worth of work, go ahead and do it when you have time to knock it off the list. Maybe when you’re feeling burnout on other projects.	04 Low	1	I spent most of 1/19 recovering almost 500 of 580 event infos/blurbs. Next Steps: Export data CSV from STAGING so we don't lose that work already done. Then I can put this on hold while higher priority projects are addressed. When we pick this back up, the next step will be importing into PROD.	10 - Partial
9	Google Apps script to copy backups to Google Workspace shared folder	Scheduled backup of ElijahStreams.com to my EricH@ElijahStreams.com account has been working fine for ten days (since 1/22), though manual copying from Google Drive to the shared Google Workspace folder is still required. I've been exploring automation solutions and it looks like the easiest solution may be a custom Google Apps script. I wrote a script that successfully copies files from one folder to another on the same Google Drive. Next steps: Test copying to a folder on a different drive. Potential roadblocks: I can foresee authentication being an issue -- I'll know more as I dig in.	(2dy-1wk)	Writing that script is pretty low priority now that the backup is happening in SOME capacity. Much more important things to work on here.	04 Low	4	1/22 Feature restored. Backs up to my EricH@ElijahStreams.com personal Google Drive folder. Then use Google Drive Desktop to copy from Google Drive to the shared Google Workspace folder. It's not ideal, but it's the best solution we have ATM. However, I'm am exploring Google Apps Script to automate copy from one drive to another. I have the copy file feature figured out and next step is to test copying from one Google Drive to Another.	10 - Partial
10	Missing thumbs on guests	On hold to work on higher priority projects. Not sure if this is actually an issue. I may have added all the thumbs a few months back, but I'll need to check to be sure.	(1-2hr)	Pretty Low priority. Fit this in between larger projects when you’re waiting on answers or are feeling burnout.	04 Low	2	Will work in around other projects	20 - Unstarted
11	AWeber subscriber count auto-update	I came across an article on AWeber yesterday that explains how to do this. The next steps is just to implement it and test. Which I can probably do tomorrow.	(1dy-1wk)	Pretty Low Priority	04 Low	3	Marked low priority	20 - Unstarted
12	Update Wells page based on Google Sheet	I have set a reminder schedule to tackle these updates on the first of each month, and I worked on this yesterday.	(2hrs-1day)	Great, looking forward to this.	02 High - Regularly Scheduled	1	2/2 - Michael liked it, but he wanted the colors changed to a single color for each country	99 - Yes
13	Plugin Auto Update Schedule	I have disabled auto-updates on all plugins. Best practice is to update plugins about a week or two after updates are released. This gives the vendors time to be informed of issues and produce fixes. However, since we have redundant backups in place, it only takes a few minutes to restore a broken site. Therefore, I recommend against a monthly update schedule in favor of updating whenever required. About every day or two WordPress tells me there are updates available, and it is not uncommon to update 2-8 plugins on any given day. However, Elementor (the "engine" that runs on top of WordPress) updates are more like once every 3 months on average - so it is the exception to the rule. The catch 22 is this: the site can break and go down because we updated a plugin that broke something, but it can also go down because we failed to update.		Okay, sounds good. Just make sure to run those updates away from show times so if the site goes down it doesn’t go down right before or after a show.	02 High - Regularly Scheduled		My Takeaway: Always do plugin updates first thing in the morning	99 - YES

## Progress 1-19 - 1-31
	EH_ELSM_20240122_TicketProgress.gsheet: Progress 1-19 - 1-31				AS OF:	January 23, 2024

Index	Project Name	Description	Time To Complete	Michael's Notes	Priority	Secondary Priority	Progress	DONE	Date Completed
1	Testimonials Page	The page and plumbing is on PROD, but hidden from the public. I probably will push the most recent version of PROD to STAGING so that we can get a better idea of where we are at. The last time I touched this was before the holiday break.	(2d-2wk)	Testimonials page is very high priority	High		1/25 - Replied to Peter's feedback - awaiting reply	partial
2	Missing event info on videos	If I have this in CSV from a previous backup I should be able to import into ES and that should take no more than 10 minutes. OTOH, if reentering the data by hand, I would just work on about 30-50 / day and could take 2-3 wks to finsh while also working on other projects.	(1hr-3wks)	Personally, I would rate the replacing missing event info as a pretty low priority item here… So, unless you’re pretty close to finishing that (less than a day worth of work) I would bump that to pretty much the bottom of this list.	Low		I spent most of 1/19 recovering almost 500 of 580 event infos/blurbs. Next Steps: Export data CSV from STAGING so we don't lose that work already done. Then I can put this on hold while higher priority projects are addressed. When we pick this back up, the next step will be importing into PROD.	partial
3	Design graphic for Featured Stories button	I have a good concept and I should be able to create the finished graphic in about an hour or so.	(1hr-1dy)	This is also really high priority	High		I should be able to get this finished by EOD today, if not sooner.	YES	2024-01-23
4	Auto-Backup to Google shared drive	We've ruled out various options and next steps is play with setting in UpdraftPlus on STAGING and test the Google addon. There is no clear solution and a custom Google App Script may be required.	(2dy-1wk)	Don’t we already have a backup solution that will backup to a normal google drive in place and operating right now? Yes, we want it to get into the Shared drive, but if we have a backup solution in place, this would be lower on the priority list.	High		1/22 Feature restored. Backs up to my EricH@ElijahStreams.com personal Google Drive folder. Then use Google Drive Desktop to copy from Google Drive to the shared Google Workspace folder. It's not ideal, but it's the best solution we have ATM. However, I'm am exploring Google Apps Script to automate copy from one drive to another. I have the copy file feature figured out and next step is to test copying from one Google Drive to Another.	YES	2024-01-22
5	Front end filtering of search results	We have the plugins we need to implement this and next steps is begin testing various solutions.	(1-2wk)	This should be near the top of the priority list along with the filtering below. I was under the impression that those two were part of the same project in all of our previous discussions…	High		1/26 - Began researching options (esp: https://www.youtube.com/watch?v=EBj7nmSxbuk&t=2211s)
6	Filters in sidebar	We have the plugins we need to implement this and next steps is begin testing various solutions.	(1-2wk)		High		1/26 - Began researching options
7	Determine how to use Git with WPE	This requires research, watching tutorials, and reading docs.	(2dy-2wk)	It seems to be that integrating GIT would make all future additions to the site MUCH faster as well as making sure there’s much less chance of data loss, right? If so, this should be a very high priority item.	High		STARTED 1/24. 1/25 - Got the WPE GitHub Actions working. Now just need to refine the rsync "FLAGS:" attribute in the YML file. / DONE. Based on my research, this is the way we should use Git version control: / Version control is only for code, not data(bases). Thus, it will only be used for custom code in plugins and themes. / We will maintain a repo for the child theme and a separate repo for a master elsms-plugin/ folder / I will do development locally, test changes and push to staging when ready to test live. / When ready to migrate the changes to staging, we will push via GitHub Actions commits (git push will trigger an automated push to staging) / When ready to push to PROD, we will use a similar git push automation as #4. If that doesn’t work for some reason, we will migrate changes by zipping the child theme or the plugin or both – wherever code changes were made – and install in WordPress admin via the normal Add Plugin > Upload button	YES	2024-01-26
8	Update Wells page based on Google Sheet	The Salleys have added some wells since last time and those need to be imported as markers into our Google map.	(2hrs-1day)	This needs to be a regularly scheduled maintenance item like we’ve previously discussed. I believe we discussed you updating this once a month around the first.	High - Regularly Scheduled		Yes, you are right. I thought I had created an recurring calendar event, but I guess not. I will create one and be able to manage these updates better. I will plan to work on this month's update later this week.
9	AWeber subscriber count auto-update	I've talked to Aweber support on the phone and they didn't have any idea how to accomplish automatically pulling the code into ES. However, I found they do have developer docs and a REST API, so the solution probably lies there or by determining what AWeber scripts were in use on the old site.	(1dy-1wk)	Pretty Low Priority	Low		Marked low priority
10	Missing thumbs on guests	Some guests were missing the photos. Need to check to see if photos still need added, or if I already resolved this.	(1-2hr)	Pretty Low priority. Fit this in between larger projects when you’re waiting on answers or are feeling burnout.	Medium		Will work in around other projects
11	Make iframe widget height auto fit	I've looked into this and think I understand the cause. The fix is probably going to related to CUSTOM CSS. It looks like a relatively quick fix, but I'll know more once I begin digging in.	(1hr-2dy)	Mid Priority, maybe fit in around other larger projects.	Medium		Will work in around other projects

## VARIABLES
VARIABLES
		STATUSES		SITE-ENV		PRIORITY LEVELS		SITE NAMES		TICKET STATUS
		10 - Partial		ES-LARDEV		01 High		ElijahStreams		⛔ Blocked
		15 - Mostly Done		ES-PROD		03 Medium		🎤 ElijahForce Podcast		🚀 In-Progress
		20 - Unstarted		ES-PROD2		04 Low		🎤 ElijahFire Podcast		✋🏻 On-Hold
		95 - Abandoned		ES-STG		60 Lowest		🎤 ElijahStreams Podcast
		99 - Complete		ES-STG2				🌐 MANY SITES
				EFORCE-PROD

## Version Log
###		Details

12	May 1, 2024	* ADD TIX: Filter for GodTalked
11	April 29, 2024	* ADD TAB: Progress 4-29 / * ADD COL: Project Family / * ADD TAB: Instructions / * Move "Key" to Instructions tab / * ADD "as of" date to Instructions tab. This will be "single source of truth" so it only needs to be changed in one place. #GOTCHA: Did not apply retroactively to old tabs, but will apply to all future progress tabs automatically.
10	April 22, 2024	* ADD TAB: Progress 4-22
9	April 16, 2024	* DELETE TAB: Quick Tix / * ADD TAB: Progress 4-16 / * DELETE abandoned items in 4-16 / * RUN APPS SCRIPT: Add filename to first cell
8	April 4, 2024	* ADD COL: Quick?
7	April 3, 2024	* ADD Variables: SITE NAMES / * ADD Trello Ticket number and status
6	March 27, 2024	* CREATE SHEET: VARIABLES / * CREATE SHEET: Progress 3/27 / * CONVERTED status, priority, and site-env to dropdown variables
5	March 11, 2024	* ADD COL: SITE-ENV / * ADD KEY
4	March 6, 2024	* CREATE SHEET: Progress 3/6 / *
3	February 2, 2024	* CREATE SHEET: Progress 2/2 / * REVISE Conditional Formatting for priorities to use REGEXMATCH()
2	January 23, 2024	* ADD COL: Date Completed
1	January 22, 2024	DOC Created